## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Orchard Amritaya
Task Name : UGR : CIVIL WORK
Plan Start Date Between 19/12/2014 To 05/12/2024 And Task Status in('Started','Completed','Non Started')
Trans Date 00:00:00 - 00:00:00
Page 1 of 1
Total Records: 55 Records 1 to 55
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | CIVIL | (M)1.5" NAIL | KG | 150 | 100 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 15000 | 15000 | UGR : CIVIL WORK | 1
2 | CIVIL | (M)10 MM DIA TMT | MT | 6.516 | 55000 | 358380 | 6.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.516 | 6.516 | 358380 | 358380 | UGR : CIVIL WORK | 1
3 | CIVIL | (M)10 MM STONE CHIPS. | MT | 275 | 1770 | 486750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 275 | 486750 | 486750 | UGR : CIVIL WORK | 1
4 | CIVIL | (M)12 MM DIA TMT | MT | 2.401 | 54500 | 130854.5 | 2.401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.401 | 2.401 | 130854.5 | 130854.5 | UGR : CIVIL WORK | 1
5 | CIVIL | (M)16 MM DIA TMT | MT | 14.044 | 54500 | 765398 | 14.044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.044 | 14.044 | 765398 | 765398 | UGR : CIVIL WORK | 1
6 | CIVIL | (M)2" NAIL | KG | 200 | 51 | 10200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 10200 | 10200 | UGR : CIVIL WORK | 1
7 | CIVIL | (M)20 mm concrete cover block | NOS | 300 | 1.78 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 534 | 534 | UGR : CIVIL WORK | 1
8 | CIVIL | (M)20 MM DIA TMT. | MT | 2.212 | 50000 | 110600 | 2.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.212 | 2.212 | 110600 | 110600 | UGR : CIVIL WORK | 1
9 | CIVIL | (M)20 MM STONE CHIPS. | MT | 280 | 1750 | 490000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 490000 | 490000 | UGR : CIVIL WORK | 1
10 | CIVIL | (M)2ND CLASS BRICKS | NOS | 11130 | 10 | 111300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11130 | 11130 | 111300 | 111300 | UGR : CIVIL WORK | 1
11 | CIVIL | (M)3" NAIL | KG | 200 | 51 | 10200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 10200 | 10200 | UGR : CIVIL WORK | 1
12 | CIVIL | (M)3" X 2"X 8'0" GOOD QUALITY HARDWOOD BATTENS (SPECIAL) | CFT | 400 | 430 | 172000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 172000 | 172000 | UGR : CIVIL WORK | 1
13 | CIVIL | (M)3"X2" Pine Batten | CFT | 100 | 767 | 76700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 76700 | 76700 | UGR : CIVIL WORK | 1
14 | CIVIL | (M)4" NAIL | KG | 100 | 51 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 5100 | 5100 | UGR : CIVIL WORK | 1
15 | CIVIL | (M)40mm Circular PVC Cover Block | NOS | 200 | 5.32 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 1064 | 1064 | UGR : CIVIL WORK | 1
16 | CIVIL | (M)50mm Concrete Cover Block | NOS | 400 | 3.54 | 1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 1416 | 1416 | UGR : CIVIL WORK | 1
17 | CIVIL | (M)50mm PVC round Cover Block | NOS | 950 | 4.14 | 3933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 950 | 3933 | 3933 | UGR : CIVIL WORK | 1
18 | CIVIL | (M)75 mm Concrete Cover Block | NOS | 350 | 4.72 | 1652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 1652 | 1652 | UGR : CIVIL WORK | 1
19 | CIVIL | (M)8 MM DIA TMT | MT | 3.7 | 56000.01 | 207200.04 | 2.957 | 2.957 | 52274 | 154574.22 | 0 | 0 | 0 | 0 | 0.743 | 3.7 | 52625.82 | 207200.04 | UGR : CIVIL WORK | 1
20 | CIVIL | (M)M.C. SAND | MT | 435 | 1711.5 | 744502.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435 | 435 | 744502.5 | 744502.5 | UGR : CIVIL WORK | 1
21 | CIVIL | (M)PICKED JHAMA. | NOS | 13400 | 11 | 147400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13400 | 13400 | 147400 | 147400 | UGR : CIVIL WORK | 1
22 | CIVIL | (M)PLY SHUTTERING OIL | LTR | 350 | 47.2 | 16520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 16520 | 16520 | UGR : CIVIL WORK | 1
23 | CIVIL | (M)POLYTHENE SHEET | KG | 180 | 110 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 19800 | 19800 | UGR : CIVIL WORK | 1
24 | CIVIL | (M)SIKAPLAST 2004 NS | KG | 1490 | 70.8 | 105492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1490 | 1490 | 105492 | 105492 | UGR : CIVIL WORK | 1
25 | VASTU | (M)12mm PLY SIZE- 8FT X 4 FT(WATER PROOF) | NOS | 115 | 2194.8 | 252402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 115 | 252402 | 252402 | UGR : CIVIL WORK | 1
26 | WATER PROOFING | (M)PPC CEMENT | BAG | 3700 | 283.59 | 1049283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3700 | 3700 | 1049283 | 1049283 | UGR : CIVIL WORK | 1
27 | CIVIL - MASONRY WORK | (L)250/230/200 MM BRICK WORK | CUM | 26 | 700 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 18200 | 18200 | UGR : CIVIL WORK | 1
28 | CIVIL SUB STRUCTURE | (L)BACK FILLING WITH EXCAVATED SOIL / SILVER SAND | CUM | 1200 | 141.6 | 169920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 169920 | 169920 | UGR : CIVIL WORK | 1
29 | CIVIL SUB STRUCTURE | (L)BED PREPARATION/ EARTH DRESSING | SQM | 510 | 82.6 | 42126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 510 | 42126 | 42126 | UGR : CIVIL WORK | 1
30 | CIVIL SUB STRUCTURE | (L)L/C for Conventional Shuttering Works | SQM | 1500 | 257 | 385500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 385500 | 385500 | UGR : CIVIL WORK | 1
31 | CIVIL SUB STRUCTURE | (L)L/C for driving Z Section Sheet Piles by Power Winch | MT | 53.295 | 5500 | 293122.5 | 0 | 53.295 | 5500 | 293122.5 | 41.76 | 41.76 | 5500 | 229680 | 0 | 11.535 | 0 | 63442.5 | UGR : CIVIL WORK | 1
32 | CIVIL SUB STRUCTURE | (L)L/C for extracting Z section Sheet Piles by Power Winch | MT | 53.295 | 5700 | 303781.5 | 0 | 53.295 | 5700 | 303781.5 | 0 | 0 | 0 | 0 | 0 | 53.295 | 0 | 303781.5 | UGR : CIVIL WORK | 1
33 | CIVIL SUB STRUCTURE | (L)L/C for Fabrication & Erection of supporting Str. Members | MT | 7 | 7000 | 49000 | 0 | 7 | 7000 | 49000 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 49000 | UGR : CIVIL WORK | 1
34 | CIVIL SUB STRUCTURE | (L)L/C for RCC M-25 Pouring in Fdn. (w/concrete pump pipeline ) | CUM | 275 | 236 | 64900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 275 | 64900 | 64900 | UGR : CIVIL WORK | 1
35 | CIVIL SUB STRUCTURE | (L)L/C for RCC Pouring in Wall/Col. incl. pipeline making | CUM | 120 | 300 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 36000 | 36000 | UGR : CIVIL WORK | 1
36 | CIVIL SUB STRUCTURE | (L)Labour Charges for Column/Wall Starter Making | RMT | 297 | 66.08 | 19625.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 297 | 19625.76 | 19625.76 | UGR : CIVIL WORK | 1
37 | CIVIL SUB STRUCTURE | (L)Labour Charges for Reinforcement Steel Work | MT | 40 | 6490 | 259600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 259600 | 259600 | UGR : CIVIL WORK | 1
38 | CIVIL SUB STRUCTURE | (L)MANUAL EXCAVATION | CUM | 152 | 206.5 | 31388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 152 | 31388 | 31388 | UGR : CIVIL WORK | 1
39 | CIVIL SUB STRUCTURE | (L)MIXING & POURING OF P.C.C.(1:3:6) | CUM | 30 | 700 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 21000 | 21000 | UGR : CIVIL WORK | 1
40 | CIVIL SUB STRUCTURE | (L)Pile Build - Up for R/F Work + Shuttering. | NOS | 46 | 118 | 5428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 5428 | 5428 | UGR : CIVIL WORK | 1
41 | CIVIL SUB STRUCTURE | (L)PILE HEAD BUILD-UP CONCRETING | NOS | 46 | 40 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 1840 | 1840 | UGR : CIVIL WORK | 1
42 | CIVIL SUB STRUCTURE | (L)PILE HEAD DISMENTLING | RMT | 231 | 500 | 115500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 231 | 115500 | 115500 | UGR : CIVIL WORK | 1
43 | CIVIL SUB STRUCTURE | (L)Supply of Skilled Labour (11 Hrs.) | MAN/DAY | 50 | 885 | 44250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 44250 | 44250 | UGR : CIVIL WORK | 1
44 | CIVIL SUPER STRUCTURE | (L)L/C for Board Making | SQM | 595.8 | 80 | 47664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.8 | 595.8 | 47664 | 47664 | UGR : CIVIL WORK | 1
45 | CIVIL SUPER STRUCTURE | (L)L/C for Cut-Out Making & Fixing (Ply) | NOS | 20 | 100 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 2000 | 2000 | UGR : CIVIL WORK | 1
46 | CIVIL SUPER STRUCTURE | (L)L/C for Staging Work (Above 3.0Mtr from Base) | CUM | 400 | 29.5 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 11800 | 11800 | UGR : CIVIL WORK | 1
47 | INFRASTRUCTURE | (L)Supply of Unskilled Labour (11 Hrs.) | MAN/DAY | 500 | 535 | 267500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 267500 | 267500 | UGR : CIVIL WORK | 1
48 | No category | (L)BRICK FLAT SOLING, SUB STRUCTURE | SQM | 376 | 50 | 18800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 376 | 18800 | 18800 | UGR : CIVIL WORK | 1
49 | No category | (L)EARTH WORK IN ALL EXCAVATION MECHANICALLY | CUM | 2630 | 305 | 802150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630 | 2630 | 802150 | 802150 | UGR : CIVIL WORK | 1
50 | No category | (L)MS SLEEVE FIXING | NOS | 30 | 320 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 9600 | 9600 | UGR : CIVIL WORK | 1
51 | R.W.H.T | (L)L/C for M-25 Grade Pouring in Col. (Head Load) | CUM | 30 | 450 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 13500 | 13500 | UGR : CIVIL WORK | 1
52 | R.W.H.T | (L)L/C for Manhole Cover Fixing | NOS | 13 | 425 | 5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 5525 | 5525 | UGR : CIVIL WORK | 1
53 | R.W.H.T | (L)L/C for Rung Ladder Fixing | NOS | 141 | 177 | 24957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 141 | 24957 | 24957 | UGR : CIVIL WORK | 1
54 | R.W.H.T | (L)L/C for Staging/Gangway for Col. & RCC Wall | CUM | 934 | 33.04 | 30859.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934 | 934 | 30859.36 | 30859.36 | UGR : CIVIL WORK | 1
55 | WEIGHMENT BRIDGE | (L)VAPOUR BARRIER | SQM | 376 | 82.6 | 31057.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 376 | 31057.6 | 31057.6 | UGR : CIVIL WORK | 1